## Checklist
OpenG2P Deployment Checklist (G2R-311)
As of 2026-10-14. Edit only the yellow cells: Owner (name), Env (dropdown: dev / staging / both), Status (dropdown), Notes.
# | Area | Check | Owner | Env | Status | Notes
1 | Repo fixes | Remove every GitLab reference: Helm repo in Jenkinsfile and upgrade.sh, registry.gitlab.com image paths, .gitlab-ci.yml, docs. `grep -rni gitlab .` empty in all 3 repos. |  |  | Not started
2 | Repo fixes | Bump registry-platform rc.544 to latest (1.2.2-rc.554) with bump-rp-version.sh; rebuild; re-run sanity. |  |  | Not started
3 | Repo fixes | Commons-services pin 2.3.0-rc.217 to 2.3.4-rc.245. |  |  | Not started
4 | Repo fixes | Remove chart-publishing leftovers from Chart.yaml (Rancher catalog annotations, CI-publish comment). |  |  | Not started
5 | Repo fixes | Parameterise hard-coded far / commons in Jenkinsfiles, ci/*, aliases, RBAC; or rename to standard names. |  |  | Not started
6 | Repo fixes | Commit per-environment values and CA bundle ConfigMap to git. |  |  | Not started
7 | Platform | Versions from OpenG2P/versions; releases only, never develop. |  |  | Not started
8 | Platform | Namespaces per OpenG2P standard; node usage under 80%. |  |  | Not started
9 | Platform | Keycloak, Postgres, MinIO, Master Data, AWE run only in <commons-ns>. |  |  | Not started
10 | Platform | 5 commons Secrets available in each <registry-ns>: commons-postgresql, commons-keycloak, master-data, commons-minio, awe-db-user. |  |  | Not started
11 | Platform | Commons-services names resolve from registry pods (commons-aliases.yaml). |  |  | Not started
12 | Registry services | Deploy from own repo chart: helm dependency build, lint / template, upgrade --install. |  |  | Not started
13 | Registry services | Livestock and crop have their own chart directories. |  |  | Not started
14 | Registry services | Images: Jenkins → ECR → Helm values (git) → helm upgrade. Dev = develop tag; staging/UAT = pinned release. |  |  | Not started
15 | Registry services | All env vars from Helm, none hand-edited in Rancher. Check COOKIE_DOMAIN, https IAM URL, app mnemonic. |  |  | Not started
16 | Registry services | Pods running: staff-api, staff-ui, partner-api, celery worker/beat, dashboard-api. |  |  | Not started
17 | Registry services | Jobs succeed: postgres-init, keycloak-init, db-seed, iam-register (tile in IAM), sanity (e2e on), reporting views. |  |  | Not started
18 | Registry services | Geo: seed-locations + one-time migrate-far-geo (dry-run first); Location dropdowns cascade. |  |  | Not started
19 | Registry services | Re-running a single Job (helm get hooks → kubectl apply) tried on dev. |  |  | Not started
20 | ODK | Decide external vs in-cluster ODK Central. |  |  | Not started
21 | ODK | Form and media published; connector reaches ODK; deployed with the right ENVIRONMENT. |  |  | Not started
22 | ODK | farmer-partner registered; ODK submission → draft intake → approval → farmer in register. |  |  | Not started
23 | DNS / TLS | Keycloak redirect URIs and cookie domain match final hosts; Local CA trusted; nginx allows 12 MB uploads on every portal. |  |  | Not started
24 | Sign-off | Staff login, intake with photo upload, AWE approval, farmer created. |  |  | Not started
25 | Sign-off | Rollback ready: Helm values backed up, revisions noted, DB snapshot taken. |  |  | Not started
Summary
| Not started | 25
| In progress | 0
| Done | 0
| Blocked | 0
| % done | 0%

## Decided
Decided standards
Agreed before the DevOps call.
Topic | Decision
Helm charts | No COSS Helm repo. Each registry's chart lives in its own repo (helm/ in farmer, livestock, crop); Jenkins deploys from the checked-out chart. No chart publishing, gh-pages, OCI push or Rancher catalog.
Source | OpenG2P is GitHub-only, no GitLab anywhere: code on github.com/OpenG2P, images on Docker Hub openg2p/*, charts from openg2p.github.io/openg2p-helm, versions from github.com/OpenG2P/versions.
Namespaces | Follow the OpenG2P standard. <commons-ns> = shared services, <registry-ns> = each registry.
Versions | Registry-platform: latest release in OpenG2P/versions (today 1.2.2-rc.554). Commons: 2.3.4-rc.245.
Commons Secrets | Handled the OpenG2P standard way, including re-sync when a password changes.

## DNS & TLS
DNS and TLS mapping
Fill the yellow cells on the call. Private hosts: host nginx (WireGuard / allowlist) → Istio internal gateway, cert from OpenG2P Local CA.
Service | Host (current or pattern) | Exposure | Final host | Resolves to | TLS cert | Verified
Farmer staff portal | farmer-registry-development.oanstaging.com | Public |  |  |  | No
Livestock staff portal | confirm | Public |  |  |  | No
Crop staff portal | confirm | Public |  |  |  | No
Internal staff hosts | staff-<registry>.<registry-ns>.openg2p.test | Private |  |  |  | No
Keycloak (public) | keycloak-development.oanstaging.com | Public |  |  |  | No
Keycloak (internal) | keycloak.<commons-ns>.openg2p.test | Private |  |  |  | No
AWE | awe.<commons-ns>.openg2p.test | Private |  |  |  | No
MinIO (pre-signed URLs) | global.minioHost, browser-resolvable | Public |  |  |  | No
ODK Central | odk-central.oanstaging.com / odk-central-development.oanstaging.com | Public |  |  |  | No
Connector UIs | connector-<registry>.<registry-ns>.openg2p.test | Private |  |  |  | No
Dashboard API | dashboard-api.<registry-ns>.openg2p.test | Private |  |  |  | No